## How to Use
How to use this construction schedule template
1. Open the 'Schedule Template' tab and enter your project name, client and project start date in the yellow cells.
2. List each task with its phase, crew or subcontractor, and duration in workdays. Blue text marks the cells you fill in.
3. In 'Depends on #', enter the row number (#) of the task that has to finish first. The start date fills in automatically.
4. Only use 'Fixed start' when a task is locked to a date (a delivery, an inspection appointment). It overrides the dependency.
5. Update 'Status' as work moves: Not started, In progress, Done or Delayed. The Gantt bars change color to match.
6. When something slips, change its duration or fixed start. Every task that depends on it moves automatically.
The 'Sample - Custom Home' tab shows a full 2,400 sq ft home build you can copy from.
Works in Excel and Google Sheets (File > Import in Sheets).
Running more than a couple of jobs at once? Projul's scheduling updates crews automatically and shows every job on one calendar: projul.com/features/scheduling/

## Schedule Template
Construction Schedule Template
Free template from Projul (projul.com). Blue cells are inputs; everything else calculates.
| Project | Project name |  | Projected finish: |  |  | 2026-11-13
| Client | Client name |  | Workdays (start to finish): |  |  | 10
| Project start date | 2026-11-02
Week of (Monday)
# | Phase | Task | Crew / Sub | Fixed start (optional) | Depends on # | Duration (workdays) | Start | End | Status | Notes | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02
1 | Pre-construction | Example: Permits and approvals (replace or delete) | Office |  |  | 10 | 2026-11-02 | 2026-11-13 | Not started | bar: 2026-11-02 to 2026-11-09
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Notes
Start = Fixed start if entered; otherwise the next workday after the task in 'Depends on #' ends; otherwise the project start date. Durations and dates skip Saturdays and Sundays.
Bars: blue = scheduled, green = done, red = delayed. The yellow column is the current week.
Note on C6: Tasks with no 'Fixed start' and no 'Depends on #' start on this date. Start and End dates skip weekends.

## Sample - Custom Home
Sample Schedule: 2,400 Sq Ft Custom Home
Free template from Projul (projul.com). Blue cells are inputs; everything else calculates.
| Project | Project name |  | Projected finish: |  |  | 2027-05-24
| Client | Client name |  | Workdays (start to finish): |  |  | 146
| Project start date | 2026-11-02
Week of (Monday)
# | Phase | Task | Crew / Sub | Fixed start (optional) | Depends on # | Duration (workdays) | Start | End | Status | Notes | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02
1 | Pre-construction | Permits, engineering and approvals | Office |  |  | 25 | 2026-11-02 | 2026-12-04 | Done | bar: 2026-11-02 to 2026-11-30
2 | Pre-construction | Order long-lead materials (windows, trusses, cabinets) | Office |  | 1 | 5 | 2026-12-07 | 2026-12-11 | Done | bar: 2026-12-07
3 | Site work | Clear, grade and excavate | Excavation sub |  | 1 | 7 | 2026-12-07 | 2026-12-15 | In progress | bar: 2026-12-07 to 2026-12-14
4 | Foundation | Footings, form and pour slab | Concrete sub |  | 3 | 8 | 2026-12-16 | 2026-12-25 | Not started | bar: 2026-12-14 to 2026-12-21
5 | Foundation | Cure, strip and waterproof | Concrete sub |  | 4 | 5 | 2026-12-28 | 2027-01-01 | Not started | bar: 2026-12-28
6 | Inspection | Foundation inspection | Inspector |  | 5 | 1 | 2027-01-04 | 2027-01-04 | Not started | bar: 2027-01-04
7 | Framing | Floor, wall and roof framing | Framing crew |  | 6 | 15 | 2027-01-05 | 2027-01-25 | Not started | bar: 2027-01-04 to 2027-01-25
8 | Framing | Sheathing, windows and exterior doors | Framing crew |  | 7 | 5 | 2027-01-26 | 2027-02-01 | Not started | bar: 2027-01-25 to 2027-02-01
9 | Roofing | Dry-in and roofing | Roofing sub |  | 8 | 5 | 2027-02-02 | 2027-02-08 | Not started | bar: 2027-02-01 to 2027-02-08
10 | Rough-ins | Rough plumbing | Plumber |  | 9 | 5 | 2027-02-09 | 2027-02-15 | Not started | bar: 2027-02-08 to 2027-02-15
11 | Rough-ins | Rough electrical | Electrician |  | 9 | 5 | 2027-02-09 | 2027-02-15 | Not started | bar: 2027-02-08 to 2027-02-15
12 | Rough-ins | Rough HVAC | HVAC sub |  | 9 | 5 | 2027-02-09 | 2027-02-15 | Not started | bar: 2027-02-08 to 2027-02-15
13 | Inspection | Rough-in and framing inspection | Inspector |  | 12 | 1 | 2027-02-16 | 2027-02-16 | Not started | bar: 2027-02-15
14 | Insulation | Insulation and insulation inspection | Insulation sub |  | 13 | 4 | 2027-02-17 | 2027-02-22 | Not started | bar: 2027-02-15 to 2027-02-22
15 | Drywall | Hang, tape and texture | Drywall sub |  | 14 | 12 | 2027-02-23 | 2027-03-10 | Not started | bar: 2027-02-22 to 2027-03-08
16 | Exterior | Siding, stone and exterior paint | Siding sub |  | 9 | 18 | 2027-02-09 | 2027-03-04 | Not started | bar: 2027-02-08 to 2027-03-01
17 | Interior | Cabinets and countertops | Cabinet installer |  | 15 | 10 | 2027-03-11 | 2027-03-24 | Not started | bar: 2027-03-08 to 2027-03-22
18 | Interior | Interior trim and doors | Finish carpenter |  | 17 | 12 | 2027-03-25 | 2027-04-09 | Not started | bar: 2027-03-22 to 2027-04-05
19 | Interior | Interior paint | Painter |  | 18 | 8 | 2027-04-12 | 2027-04-21 | Not started | bar: 2027-04-12 to 2027-04-19
20 | Interior | Flooring | Flooring sub |  | 19 | 8 | 2027-04-22 | 2027-05-03 | Not started | bar: 2027-04-19 to 2027-05-03
21 | Mechanical trim | Fixtures, devices and HVAC trim-out | Plumber / Electrician / HVAC |  | 20 | 5 | 2027-05-04 | 2027-05-10 | Not started | bar: 2027-05-03 to 2027-05-10
22 | Site work | Flatwork, driveway and landscaping | Concrete sub / Landscaper |  | 16 | 12 | 2027-03-05 | 2027-03-22 | Not started | bar: 2027-03-01 to 2027-03-22
23 | Closeout | Final clean and punch list | GC crew |  | 21 | 7 | 2027-05-11 | 2027-05-19 | Not started | bar: 2027-05-10 to 2027-05-17
24 | Inspection | Final inspections and certificate of occupancy | Inspector |  | 23 | 3 | 2027-05-20 | 2027-05-24 | Not started | bar: 2027-05-17 to 2027-05-24
Notes
Start = Fixed start if entered; otherwise the next workday after the task in 'Depends on #' ends; otherwise the project start date. Durations and dates skip Saturdays and Sundays.
Bars: blue = scheduled, green = done, red = delayed. The yellow column is the current week.
Durations are typical for a slab-on-grade, stick-frame home and are examples only. Adjust them for your crews, subs, inspections and climate.
Note on C6: Tasks with no 'Fixed start' and no 'Depends on #' start on this date. Start and End dates skip weekends.